## Instructions
MMTPL Contract Dataset — How to use this workbook
1. Fill one row per historical contract in the 'Contract_Data' sheet.
2. Columns A-P (white) are FEATURES — known at the bidding/planning stage,
before the contract is executed. This is what a new prediction will be based on.
3. Columns Q-W (shaded grey) are TARGETS/OUTCOMES — only known after the contract
finished or is well underway. These are what the model learns to predict.
4. Leave a cell blank only if truly unknown — do not guess. Missing target values
for old contracts still let you use that row for other purposes, but a row with no
targets filled in cannot be used for training.
5. See 'Data_Dictionary' sheet for what each column means and allowed values.
6. Row 2 in Contract_Data is a filled EXAMPLE (grey italic text) — do not train on it,
delete it once you understand the format, or keep it as a reference at the top.
How many rows do you need?
Minimum to even attempt a model: ~60-80 contracts (expect a weak, high-variance model)
Reasonable first working model: 150-250 contracts
Comfortable / good generalization: 400-600+ contracts
More detail on this is in the chat response.

## Contract_Data
Contract_ID | Client_Name | Client_Industry | Plant_Location | Plant_Unit_Type | Contract_Type | Contract_Nature | Scope_Summary | Est_Equipment_Weight_Tons | Est_Contract_Value_INR_Lakhs | Planned_Duration_Days | Site_Distance_From_Base_KM | Shifts_Planned | Safety_Risk_Level | Repeat_Client | Season_of_Start | Actual_Peak_Manpower | Actual_Avg_Monthly_Manpower | Skilled_Manpower_Percent | Actual_Duration_Days | Actual_Cost_INR_Lakhs | Delay_Days | Contract_Outcome
MMTPL-2015-001 | Tata Steel | Steel | Jamshedpur, Jharkhand | Coke Oven | Fabrication & Erection | New Installation | Fabrication & Erection of Coke Oven equipment | 3286 | 2097 | 527 | 1136 | 1 | Medium | Yes | Monsoon | 125 | 88 | 65 | 135 | 921 | -392 | Terminated Early
MMTPL-2015-002 | AMNS India | Steel | Hazira, Gujarat | Sinter Plant | Structural Steel | Revamp | Structural Steel of Sinter Plant equipment | 2778 | 1887 | 297 | 346 | 1 | Medium | Yes | Monsoon | 188 | 118 | 52 | 391 | 2398 | 94 | Completed Delayed
MMTPL-2015-003 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Rolling Mill | AMC | Maintenance | AMC of Rolling Mill equipment | 167 | 94 | 365 | 795 | 1 | Medium | Yes | Monsoon | 47 | 29 | 42 | 365 | 95 | 0 | Completed On-Time
MMTPL-2015-004 | Tata Steel | Steel | Jamshedpur, Jharkhand | Sinter Plant | Revamp | Revamp | Revamp of Sinter Plant equipment | 2870 | 2104 | 110 | 798 | 1 | Medium | Yes | Winter | 522 | 389 | 73 | 129 | 2592 | 19 | Completed Delayed
MMTPL-2015-005 | Tata Steel | Steel | Jamshedpur, Jharkhand | Other (SMS) | AMC | Maintenance | AMC of Other (SMS) equipment | 112 | 42 | 365 | 797 | 1 | High | Yes | Winter | 30 | 23 | 33 | 365 | 40 | 0 | Completed On-Time
MMTPL-2015-006 | AMNS India | Steel | Hazira, Gujarat | Coke Oven | Structural Steel | Maintenance | Structural Steel of Coke Oven equipment | 471 | 191 | 114 | 1042 | 2 | Medium | Yes | Winter | 166 | 98 | 67 | 129 | 223 | 15 | Completed Delayed
MMTPL-2015-007 | Vedanta | Mining | Jharsuguda, Odisha | Material Handling | Fabrication & Erection | New Installation | Fabrication & Erection of Material Handling equipment | 9348 | 6336 | 402 | 244 | 1 | Low | Yes | Winter | 466 | 319 | 65 | 475 | 8230 | 73 | Completed Delayed
MMTPL-2015-008 | JSW Steel | Steel | Bellary, Karnataka | Other (SMS) | Revamp | Revamp | Revamp of Other (SMS) equipment | 2685 | 955 | 286 | 910 | 2 | High | Yes | Summer | 376 | 211 | 36 | 264 | 859 | -22 | Completed On-Time
MMTPL-2015-009 | Jindal Steel | Steel | Angul, Odisha | Sinter Plant | Piping | New Installation | Piping of Sinter Plant equipment | 9837 | 5897 | 548 | 1020 | 1 | Medium | Yes | Monsoon | 360 | 290 | 35 | 634 | 6540 | 86 | Completed Delayed
MMTPL-2015-010 | Tata Steel | Steel | Kalinganagar, Odisha | Blast Furnace | Revamp | Revamp | Revamp of Blast Furnace equipment | 4863 | 1771 | 286 | 993 | 1 | High | No | Summer | 341 | 234 | 74 | 269 | 1552 | -17 | Completed On-Time
MMTPL-2015-011 | AMNS India | Steel | Hazira, Gujarat | Rolling Mill | AMC | Maintenance | AMC of Rolling Mill equipment | 216 | 105 | 365 | 1079 | 1 | Medium | Yes | Summer | 38 | 26 | 67 | 365 | 103 | 0 | Completed On-Time
MMTPL-2015-012 | AMNS India | Steel | Hazira, Gujarat | Blast Furnace | AMC | Maintenance | AMC of Blast Furnace equipment | 211 | 69 | 365 | 158 | 1 | High | No | Monsoon | 41 | 27 | 64 | 365 | 67 | 0 | Completed On-Time
MMTPL-2015-013 | SAIL | Steel | Bokaro, Jharkhand | Other (SMS) | Shutdown Maintenance | Breakdown-Emergency | Shutdown Maintenance of Other (SMS) equipment | 597 | 235 | 45 | 218 | 3 | High | Yes | Monsoon | 796 | 672 | 36 | 58 | 318 | 13 | Completed Delayed
MMTPL-2015-014 | JSW Steel | Steel | Dolvi, Maharashtra | Coke Oven | Revamp | Revamp | Revamp of Coke Oven equipment | 1395 | 551 | 153 | 938 | 1 | Medium | Yes | Summer | 183 | 146 | 65 | 210 | 768 | 57 | Completed Delayed
MMTPL-2015-015 | Tata Steel | Steel | Jamshedpur, Jharkhand | Other (SMS) | Revamp | Revamp | Revamp of Other (SMS) equipment | 620 | 237 | 113 | 1014 | 1 | High | Yes | Monsoon | 110 | 90 | 59 | 118 | 249 | 5 | Completed Delayed
MMTPL-2015-016 | Jindal Steel | Steel | Raigarh, Chhattisgarh | Other (SMS) | AMC | Maintenance | AMC of Other (SMS) equipment | 233 | 126 | 365 | 408 | 1 | High | Yes | Summer | 43 | 26 | 33 | 365 | 126 | 0 | Completed On-Time
MMTPL-2015-017 | UltraTech Cement | Cement | Hirmi, Chhattisgarh | Material Handling | Mechanical Erection | Revamp | Mechanical Erection of Material Handling equipment | 1156 | 690 | 137 | 1402 | 1 | Low | Yes | Winter | 169 | 119 | 63 | 173 | 882 | 36 | Completed Delayed
MMTPL-2015-018 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Rolling Mill | AMC | Maintenance | AMC of Rolling Mill equipment | 233 | 106 | 365 | 563 | 1 | Medium | Yes | Winter | 49 | 37 | 34 | 365 | 105 | 0 | Completed On-Time
MMTPL-2015-019 | JSW Steel | Steel | Dolvi, Maharashtra | Other (SMS) | Shutdown Maintenance | Shutdown | Shutdown Maintenance of Other (SMS) equipment | 250 | 138 | 49 | 291 | 2 | High | No | Summer | 205 | 152 | 69 | 54 | 163 | 5 | Completed Delayed
MMTPL-2015-020 | NTPC | Power | Korba, Chhattisgarh | Material Handling | AMC | Maintenance | AMC of Material Handling equipment | 76 | 58 | 365 | 295 | 1 | Medium | Yes | Summer | 29 | 20 | 75 | 365 | 56 | 0 | Completed On-Time
MMTPL-2015-021 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Other (Smelter) | Shutdown Maintenance | Breakdown-Emergency | Shutdown Maintenance of Other (Smelter) equipment | 614 | 378 | 18 | 586 | 2 | Low | Yes | Summer | 1365 | 886 | 30 | 23 | 498 | 5 | Completed Delayed
MMTPL-2015-022 | Tata Steel | Steel | Jamshedpur, Jharkhand | Sinter Plant | Shutdown Maintenance | Shutdown | Shutdown Maintenance of Sinter Plant equipment | 856 | 440 | 52 | 105 | 2 | Medium | Yes | Summer | 659 | 509 | 56 | 59 | 481 | 7 | Completed Delayed
MMTPL-2016-023 | UltraTech Cement | Cement | Hirmi, Chhattisgarh | Material Handling | Revamp | Revamp | Revamp of Material Handling equipment | 1831 | 1356 | 294 | 70 | 1 | Low | Yes | Monsoon | 125 | 73 | 40 | 377 | 1843 | 83 | Completed Delayed
MMTPL-2016-024 | Tata Steel | Steel | Kalinganagar, Odisha | Blast Furnace | Revamp | Revamp | Revamp of Blast Furnace equipment | 4355 | 3084 | 146 | 962 | 1 | High | Yes | Summer | 597 | 313 | 47 | 137 | 2725 | -9 | Completed On-Time
MMTPL-2016-025 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Other (Smelter) | Mechanical Erection | New Installation | Mechanical Erection of Other (Smelter) equipment | 5279 | 1684 | 241 | 1241 | 2 | Medium | Yes | Monsoon | 877 | 496 | 32 | 262 | 1986 | 21 | Completed Delayed
MMTPL-2016-026 | Vedanta | Mining | Jharsuguda, Odisha | Beneficiation Plant | Piping | Maintenance | Piping of Beneficiation Plant equipment | 486 | 307 | 144 | 275 | 2 | Medium | Yes | Winter | 135 | 87 | 54 | 166 | 342 | 22 | Completed Delayed
MMTPL-2016-027 | SAIL | Steel | Bokaro, Jharkhand | Other (SMS) | Piping | Maintenance | Piping of Other (SMS) equipment | 2444 | 1083 | 60 | 900 | 2 | High | No | Winter | 1242 | 966 | 40 | 72 | 1276 | 12 | Completed Delayed
MMTPL-2016-028 | Tata Steel | Steel | Kalinganagar, Odisha | Other (SMS) | AMC | Maintenance | AMC of Other (SMS) equipment | 212 | 129 | 365 | 211 | 1 | High | No | Summer | 26 | 14 | 32 | 365 | 125 | 0 | Completed On-Time
MMTPL-2016-029 | AMNS India | Steel | Hazira, Gujarat | Other (SMS) | Revamp | Revamp | Revamp of Other (SMS) equipment | 1096 | 814 | 206 | 1198 | 2 | High | Yes | Winter | 213 | 173 | 36 | 226 | 940 | 20 | Completed Delayed
MMTPL-2016-030 | Vedanta | Mining | Jharsuguda, Odisha | Beneficiation Plant | Revamp | Revamp | Revamp of Beneficiation Plant equipment | 4743 | 2744 | 208 | 268 | 1 | Medium | Yes | Monsoon | 457 | 371 | 69 | 261 | 3761 | 53 | Completed Delayed
MMTPL-2016-031 | NTPC | Power | Vindhyachal, MP | Material Handling | Fabrication & Erection | Revamp | Fabrication & Erection of Material Handling equipment | 4388 | 2965 | 205 | 1325 | 2 | Medium | No | Winter | 857 | 498 | 51 | 246 | 3760 | 41 | Completed Delayed
MMTPL-2016-032 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Rolling Mill | Fabrication & Erection | New Installation | Fabrication & Erection of Rolling Mill equipment | 7275 | 4752 | 505 | 151 | 1 | Medium | Yes | Monsoon | 289 | 236 | 67 | 566 | 5395 | 61 | Completed Delayed
MMTPL-2016-033 | JSW Steel | Steel | Dolvi, Maharashtra | Rolling Mill | Mechanical Erection | Maintenance | Mechanical Erection of Rolling Mill equipment | 1423 | 809 | 159 | 1138 | 2 | Medium | No | Summer | 358 | 262 | 55 | 193 | 990 | 34 | Completed Delayed
MMTPL-2016-034 | SAIL | Steel | Rourkela, Odisha | Sinter Plant | Shutdown Maintenance | Shutdown | Shutdown Maintenance of Sinter Plant equipment | 906 | 309 | 52 | 897 | 2 | Medium | Yes | Monsoon | 697 | 430 | 54 | 60 | 363 | 8 | Completed Delayed
MMTPL-2016-035 | Jindal Steel | Steel | Raigarh, Chhattisgarh | Coke Oven | Revamp | Revamp | Revamp of Coke Oven equipment | 1170 | 789 | 210 | 126 | 1 | Medium | No | Monsoon | 112 | 57 | 45 | 290 | 1041 | 80 | Completed Delayed
MMTPL-2016-036 | AMNS India | Steel | Hazira, Gujarat | Other (SMS) | Fabrication & Erection | New Installation | Fabrication & Erection of Other (SMS) equipment | 3068 | 1785 | 392 | 466 | 1 | High | Yes | Monsoon | 157 | 84 | 40 | 494 | 2389 | 102 | Completed Delayed
MMTPL-2016-037 | Jindal Steel | Steel | Angul, Odisha | Other (SMS) | Mechanical Erection | Maintenance | Mechanical Erection of Other (SMS) equipment | 2558 | 1971 | 156 | 426 | 2 | High | Yes | Winter | 656 | 485 | 37 | 201 | 2527 | 45 | Completed Delayed
MMTPL-2016-038 | UltraTech Cement | Cement | Hirmi, Chhattisgarh | Other (Kiln) | Shutdown Maintenance | Breakdown-Emergency | Shutdown Maintenance of Other (Kiln) equipment | 1454 | 804 | 38 | 718 | 2 | Low | No | Monsoon | 1362 | 753 | 41 | 48 | 1091 | 10 | Completed Delayed
MMTPL-2016-039 | NTPC | Power | Vindhyachal, MP | Material Handling | Structural Steel | Maintenance | Structural Steel of Material Handling equipment | 2626 | 1906 | 128 | 197 | 2 | Medium | No | Summer | 821 | 552 | 50 | 164 | 2443 | 36 | Completed Delayed
MMTPL-2016-040 | SAIL | Steel | Rourkela, Odisha | Sinter Plant | Piping | Maintenance | Piping of Sinter Plant equipment | 1594 | 921 | 131 | 1078 | 2 | Medium | No | Summer | 487 | 324 | 75 | 163 | 1129 | 32 | Completed Delayed
MMTPL-2016-041 | Hindalco | Metals & Alloys | Renukoot, UP | Rolling Mill | Mechanical Erection | Maintenance | Mechanical Erection of Rolling Mill equipment | 1107 | 501 | 163 | 1211 | 1 | Medium | Yes | Winter | 136 | 101 | 47 | 213 | 654 | 50 | Completed Delayed
MMTPL-2016-042 | Jindal Steel | Steel | Raigarh, Chhattisgarh | Sinter Plant | Mechanical Erection | Revamp | Mechanical Erection of Sinter Plant equipment | 2077 | 1394 | 170 | 1433 | 1 | Medium | Yes | Summer | 245 | 173 | 36 | 213 | 1858 | 43 | Completed Delayed
MMTPL-2016-043 | AMNS India | Steel | Hazira, Gujarat | Sinter Plant | Piping | New Installation | Piping of Sinter Plant equipment | 5952 | 2601 | 157 | 131 | 1 | Medium | Yes | Winter | 759 | 382 | 48 | 153 | 2320 | -4 | Completed On-Time
MMTPL-2016-044 | Hindalco | Metals & Alloys | Renukoot, UP | Other (Smelter) | Piping | New Installation | Piping of Other (Smelter) equipment | 1841 | 657 | 279 | 153 | 2 | Medium | Yes | Winter | 264 | 160 | 45 | 307 | 747 | 28 | Completed Delayed
MMTPL-2017-045 | Tata Steel | Steel | Kalinganagar, Odisha | Other (SMS) | Shutdown Maintenance | Shutdown | Shutdown Maintenance of Other (SMS) equipment | 1170 | 882 | 39 | 628 | 3 | High | No | Monsoon | 1485 | 1138 | 70 | 49 | 1175 | 10 | Completed Delayed
MMTPL-2017-046 | AMNS India | Steel | Hazira, Gujarat | Blast Furnace | Fabrication & Erection | New Installation | Fabrication & Erection of Blast Furnace equipment | 3847 | 1455 | 432 | 856 | 1 | High | Yes | Winter | 179 | 143 | 34 | 497 | 1661 | 65 | Completed Delayed
MMTPL-2017-047 | AMNS India | Steel | Hazira, Gujarat | Other (SMS) | AMC | Maintenance | AMC of Other (SMS) equipment | 255 | 195 | 365 | 890 | 1 | High | Yes | Summer | 46 | 25 | 33 | 365 | 202 | 0 | Completed On-Time
MMTPL-2017-048 | SAIL | Steel | Rourkela, Odisha | Other (SMS) | AMC | Maintenance | AMC of Other (SMS) equipment | 261 | 152 | 365 | 611 | 1 | High | Yes | Monsoon | 50 | 29 | 64 | 365 | 155 | 0 | Completed On-Time
MMTPL-2017-049 | Hindalco | Metals & Alloys | Renukoot, UP | Rolling Mill | Shutdown Maintenance | Shutdown | Shutdown Maintenance of Rolling Mill equipment | 984 | 307 | 35 | 488 | 3 | Medium | No | Winter | 1295 | 665 | 41 | 46 | 433 | 11 | Completed Delayed
MMTPL-2017-050 | Hindalco | Metals & Alloys | Renukoot, UP | Other (Smelter) | Fabrication & Erection | Revamp | Fabrication & Erection of Other (Smelter) equipment | 4070 | 3193 | 252 | 982 | 2 | Medium | Yes | Monsoon | 647 | 388 | 55 | 293 | 3913 | 41 | Completed Delayed
MMTPL-2017-051 | NTPC | Power | Korba, Chhattisgarh | Material Handling | Mechanical Erection | Maintenance | Mechanical Erection of Material Handling equipment | 1233 | 968 | 142 | 847 | 1 | Low | Yes | Winter | 174 | 117 | 58 | 174 | 1237 | 32 | Completed Delayed
MMTPL-2017-052 | JSW Steel | Steel | Bellary, Karnataka | Coke Oven | Shutdown Maintenance | Shutdown | Shutdown Maintenance of Coke Oven equipment | 689 | 248 | 43 | 1310 | 3 | Medium | Yes | Summer | 962 | 556 | 37 | 45 | 262 | 2 | Completed Delayed
MMTPL-2017-053 | Hindalco | Metals & Alloys | Renukoot, UP | Rolling Mill | Structural Steel | Revamp | Structural Steel of Rolling Mill equipment | 2890 | 1467 | 220 | 1008 | 2 | Medium | No | Summer | 526 | 400 | 38 | 245 | 1698 | 25 | Completed Delayed
MMTPL-2017-054 | Tata Steel | Steel | Kalinganagar, Odisha | Rolling Mill | Piping | Revamp | Piping of Rolling Mill equipment | 2688 | 1186 | 300 | 631 | 1 | Medium | No | Winter | 180 | 111 | 65 | 330 | 1344 | 30 | Completed Delayed
MMTPL-2017-055 | NTPC | Power | Vindhyachal, MP | Material Handling | Piping | New Installation | Piping of Material Handling equipment | 4912 | 2047 | 442 | 861 | 2 | Low | Yes | Monsoon | 445 | 350 | 39 | 523 | 2542 | 81 | Completed Delayed
MMTPL-2017-056 | Hindalco | Metals & Alloys | Renukoot, UP | Rolling Mill | Shutdown Maintenance | Breakdown-Emergency | Shutdown Maintenance of Rolling Mill equipment | 305 | 171 | 43 | 955 | 2 | Medium | Yes | Summer | 284 | 238 | 51 | 39 | 150 | -4 | Completed On-Time
MMTPL-2017-057 | UltraTech Cement | Cement | Hirmi, Chhattisgarh | Material Handling | Revamp | Revamp | Revamp of Material Handling equipment | 3191 | 2479 | 262 | 1303 | 2 | Medium | No | Summer | 488 | 282 | 35 | 337 | 3166 | 75 | Completed Delayed
MMTPL-2017-058 | Vedanta | Mining | Jharsuguda, Odisha | Beneficiation Plant | Structural Steel | New Installation | Structural Steel of Beneficiation Plant equipment | 5906 | 2729 | 164 | 134 | 1 | Medium | Yes | Monsoon | 721 | 403 | 35 | 204 | 3628 | 40 | Completed Delayed
MMTPL-2017-059 | UltraTech Cement | Cement | Hirmi, Chhattisgarh | Material Handling | Structural Steel | Revamp | Structural Steel of Material Handling equipment | 1672 | 1034 | 149 | 961 | 2 | Medium | Yes | Monsoon | 449 | 278 | 67 | 164 | 1156 | 15 | Completed Delayed
MMTPL-2017-060 | Jindal Steel | Steel | Raigarh, Chhattisgarh | Coke Oven | Structural Steel | Maintenance | Structural Steel of Coke Oven equipment | 1015 | 358 | 158 | 801 | 2 | Medium | Yes | Winter | 257 | 164 | 30 | 142 | 329 | -16 | Completed On-Time
MMTPL-2017-061 | UltraTech Cement | Cement | Hirmi, Chhattisgarh | Other (Kiln) | Revamp | Revamp | Revamp of Other (Kiln) equipment | 2844 | 1716 | 288 | 741 | 1 | Low | Yes | Winter | 198 | 108 | 36 | 281 | 1677 | -7 | Completed On-Time
MMTPL-2017-062 | JSW Steel | Steel | Dolvi, Maharashtra | Rolling Mill | Mechanical Erection | Revamp | Mechanical Erection of Rolling Mill equipment | 3488 | 1203 | 277 | 624 | 1 | Medium | Yes | Monsoon | 252 | 172 | 47 | 343 | 1632 | 66 | Completed Delayed
MMTPL-2017-063 | SAIL | Steel | Rourkela, Odisha | Rolling Mill | Revamp | Revamp | Revamp of Rolling Mill equipment | 2917 | 2048 | 281 | 979 | 2 | Medium | No | Summer | 416 | 265 | 65 | 361 | 2765 | 80 | Completed Delayed
MMTPL-2017-064 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Other (Smelter) | Mechanical Erection | Maintenance | Mechanical Erection of Other (Smelter) equipment | 2397 | 1160 | 91 | 1396 | 2 | Medium | Yes | Winter | 1054 | 853 | 65 | 102 | 1240 | 11 | Completed Delayed
MMTPL-2017-065 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Rolling Mill | AMC | Maintenance | AMC of Rolling Mill equipment | 260 | 138 | 365 | 1455 | 1 | Medium | Yes | Monsoon | 21 | 12 | 61 | 365 | 131 | 0 | Completed On-Time
MMTPL-2017-066 | Tata Steel | Steel | Jamshedpur, Jharkhand | Sinter Plant | Shutdown Maintenance | Shutdown | Shutdown Maintenance of Sinter Plant equipment | 895 | 568 | 44 | 1446 | 3 | Medium | No | Monsoon | 1221 | 966 | 69 | 59 | 798 | 15 | Completed Delayed
MMTPL-2018-067 | Vedanta | Mining | Jharsuguda, Odisha | Beneficiation Plant | AMC | Maintenance | AMC of Beneficiation Plant equipment | 144 | 58 | 365 | 930 | 1 | Low | No | Summer | 48 | 40 | 52 | 365 | 57 | 0 | Completed On-Time
MMTPL-2018-068 | JSW Steel | Steel | Dolvi, Maharashtra | Coke Oven | Fabrication & Erection | New Installation | Fabrication & Erection of Coke Oven equipment | 8450 | 5246 | 196 | 1242 | 1 | Medium | No | Summer | 863 | 452 | 65 | 214 | 5926 | 18 | Completed Delayed
MMTPL-2018-069 | AMNS India | Steel | Hazira, Gujarat | Sinter Plant | Piping | New Installation | Piping of Sinter Plant equipment | 1046 | 830 | 291 | 1126 | 1 | Medium | Yes | Summer | 72 | 55 | 67 | 265 | 720 | -26 | Completed On-Time
MMTPL-2018-070 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Rolling Mill | Piping | New Installation | Piping of Rolling Mill equipment | 3076 | 1731 | 529 | 150 | 2 | Medium | Yes | Monsoon | 233 | 120 | 72 | 648 | 2315 | 119 | Completed Delayed
MMTPL-2018-071 | NTPC | Power | Vindhyachal, MP | Material Handling | AMC | Maintenance | AMC of Material Handling equipment | 296 | 93 | 365 | 1000 | 1 | Medium | Yes | Summer | 22 | 17 | 50 | 365 | 96 | 0 | Completed On-Time
MMTPL-2018-072 | UltraTech Cement | Cement | Hirmi, Chhattisgarh | Material Handling | Fabrication & Erection | Maintenance | Fabrication & Erection of Material Handling equipment | 2757 | 1352 | 200 | 1243 | 2 | Medium | Yes | Winter | 552 | 445 | 65 | 182 | 1228 | -18 | Completed On-Time
MMTPL-2018-073 | AMNS India | Steel | Hazira, Gujarat | Rolling Mill | Fabrication & Erection | Maintenance | Fabrication & Erection of Rolling Mill equipment | 1588 | 806 | 176 | 214 | 2 | Medium | Yes | Monsoon | 361 | 188 | 35 | 194 | 967 | 18 | Completed Delayed
MMTPL-2018-074 | Tata Steel | Steel | Kalinganagar, Odisha | Blast Furnace | AMC | Maintenance | AMC of Blast Furnace equipment | 239 | 116 | 365 | 286 | 1 | High | Yes | Winter | 41 | 22 | 52 | 365 | 116 | 0 | Completed On-Time
MMTPL-2018-075 | Vedanta | Mining | Jharsuguda, Odisha | Material Handling | Shutdown Maintenance | Breakdown-Emergency | Shutdown Maintenance of Material Handling equipment | 820 | 309 | 21 | 1007 | 2 | Low | No | Monsoon | 1413 | 918 | 65 | 27 | 411 | 6 | Completed Delayed
MMTPL-2018-076 | UltraTech Cement | Cement | Hirmi, Chhattisgarh | Other (Kiln) | Mechanical Erection | New Installation | Mechanical Erection of Other (Kiln) equipment | 5477 | 4166 | 509 | 738 | 2 | Low | Yes | Summer | 431 | 220 | 63 | 559 | 4781 | 50 | Completed Delayed
MMTPL-2018-077 | AMNS India | Steel | Hazira, Gujarat | Rolling Mill | Structural Steel | Maintenance | Structural Steel of Rolling Mill equipment | 844 | 557 | 154 | 1182 | 2 | Medium | Yes | Summer | 220 | 144 | 57 | 139 | 458 | -15 | Completed On-Time
MMTPL-2018-078 | Hindalco | Metals & Alloys | Renukoot, UP | Other (Smelter) | Piping | New Installation | Piping of Other (Smelter) equipment | 9394 | 4837 | 208 | 600 | 2 | Medium | Yes | Monsoon | 1003 | 573 | 43 | 90 | 3190 | -118 | Terminated Early
MMTPL-2018-079 | SAIL | Steel | Rourkela, Odisha | Coke Oven | Piping | New Installation | Piping of Coke Oven equipment | 1126 | 436 | 404 | 798 | 2 | Medium | Yes | Summer | 112 | 89 | 32 | 396 | 389 | -8 | Completed On-Time
MMTPL-2018-080 | Vedanta | Mining | Jharsuguda, Odisha | Material Handling | Mechanical Erection | Maintenance | Mechanical Erection of Material Handling equipment | 2558 | 1674 | 169 | 875 | 2 | Medium | Yes | Summer | 606 | 449 | 53 | 233 | 2351 | 64 | Completed Delayed
MMTPL-2018-081 | Tata Steel | Steel | Kalinganagar, Odisha | Blast Furnace | Fabrication & Erection | Maintenance | Fabrication & Erection of Blast Furnace equipment | 2612 | 1300 | 162 | 655 | 1 | High | Yes | Summer | 323 | 219 | 52 | 199 | 1544 | 37 | Completed Delayed
MMTPL-2018-082 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Rolling Mill | Mechanical Erection | New Installation | Mechanical Erection of Rolling Mill equipment | 5193 | 3122 | 251 | 1362 | 1 | Medium | Yes | Winter | 414 | 340 | 66 | 244 | 2935 | -7 | Completed On-Time
MMTPL-2018-083 | UltraTech Cement | Cement | Hirmi, Chhattisgarh | Other (Kiln) | Fabrication & Erection | Maintenance | Fabrication & Erection of Other (Kiln) equipment | 479 | 294 | 180 | 582 | 2 | Low | Yes | Summer | 107 | 56 | 35 | 192 | 337 | 12 | Completed Delayed
MMTPL-2018-084 | UltraTech Cement | Cement | Hirmi, Chhattisgarh | Other (Kiln) | Shutdown Maintenance | Shutdown | Shutdown Maintenance of Other (Kiln) equipment | 1021 | 470 | 51 | 994 | 2 | Low | No | Monsoon | 801 | 541 | 41 | 59 | 574 | 8 | Completed Delayed
MMTPL-2018-085 | JSW Steel | Steel | Bellary, Karnataka | Rolling Mill | Structural Steel | Revamp | Structural Steel of Rolling Mill equipment | 4782 | 2304 | 246 | 599 | 1 | Medium | Yes | Monsoon | 389 | 239 | 65 | 312 | 2922 | 66 | Completed Delayed
MMTPL-2018-086 | Vedanta | Mining | Jharsuguda, Odisha | Material Handling | AMC | Maintenance | AMC of Material Handling equipment | 268 | 168 | 365 | 1254 | 1 | Low | Yes | Winter | 29 | 24 | 74 | 365 | 175 | 0 | Completed On-Time
MMTPL-2018-087 | Vedanta | Mining | Jharsuguda, Odisha | Beneficiation Plant | Piping | Revamp | Piping of Beneficiation Plant equipment | 3585 | 2533 | 254 | 1392 | 2 | Low | Yes | Monsoon | 565 | 350 | 61 | 294 | 3203 | 40 | Completed Delayed
MMTPL-2018-088 | AMNS India | Steel | Hazira, Gujarat | Sinter Plant | Fabrication & Erection | New Installation | Fabrication & Erection of Sinter Plant equipment | 5846 | 3237 | 582 | 1125 | 1 | Medium | No | Winter | 201 | 109 | 54 | 233 | 2459 | -349 | Terminated Early
MMTPL-2019-089 | SAIL | Steel | Bhilai, Chhattisgarh | Sinter Plant | Revamp | Revamp | Revamp of Sinter Plant equipment | 1856 | 597 | 274 | 766 | 2 | Medium | Yes | Summer | 271 | 157 | 45 | 267 | 591 | -7 | Completed On-Time
MMTPL-2019-090 | Jindal Steel | Steel | Raigarh, Chhattisgarh | Sinter Plant | Piping | Revamp | Piping of Sinter Plant equipment | 4109 | 2831 | 208 | 1049 | 2 | Medium | Yes | Summer | 791 | 573 | 53 | 190 | 2424 | -18 | Completed On-Time
MMTPL-2019-091 | NTPC | Power | Korba, Chhattisgarh | Power-Boiler House | Piping | New Installation | Piping of Power-Boiler House equipment | 3626 | 2729 | 289 | 321 | 2 | High | No | Summer | 502 | 255 | 33 | 349 | 3303 | 60 | Completed Delayed
MMTPL-2019-092 | Vedanta | Mining | Jharsuguda, Odisha | Beneficiation Plant | Structural Steel | New Installation | Structural Steel of Beneficiation Plant equipment | 7142 | 3280 | 264 | 222 | 1 | Medium | No | Summer | 542 | 428 | 75 | 198 | 1913 | -66 | Terminated Early
MMTPL-2019-093 | Hindalco | Metals & Alloys | Renukoot, UP | Rolling Mill | Mechanical Erection | New Installation | Mechanical Erection of Rolling Mill equipment | 5193 | 2982 | 260 | 1266 | 1 | Medium | Yes | Summer | 400 | 289 | 69 | 284 | 3210 | 24 | Completed Delayed
MMTPL-2019-094 | Hindalco | Metals & Alloys | Renukoot, UP | Rolling Mill | Revamp | Revamp | Revamp of Rolling Mill equipment | 4594 | 2829 | 242 | 1197 | 1 | Medium | Yes | Summer | 380 | 214 | 72 | 283 | 3426 | 41 | Completed Delayed
MMTPL-2019-095 | Tata Steel | Steel | Kalinganagar, Odisha | Blast Furnace | Shutdown Maintenance | Shutdown | Shutdown Maintenance of Blast Furnace equipment | 899 | 555 | 45 | 784 | 2 | High | Yes | Summer | 800 | 429 | 67 | 51 | 659 | 6 | Completed Delayed
MMTPL-2019-096 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Rolling Mill | Piping | Revamp | Piping of Rolling Mill equipment | 3273 | 2340 | 298 | 1422 | 1 | Medium | Yes | Winter | 220 | 182 | 32 | 326 | 2706 | 28 | Completed Delayed
MMTPL-2019-097 | Jindal Steel | Steel | Angul, Odisha | Blast Furnace | Revamp | Revamp | Revamp of Blast Furnace equipment | 2134 | 1636 | 100 | 1075 | 2 | High | Yes | Winter | 854 | 684 | 33 | 127 | 2063 | 27 | Completed Delayed
MMTPL-2019-098 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Rolling Mill | Revamp | Revamp | Revamp of Rolling Mill equipment | 3514 | 2360 | 201 | 811 | 2 | Medium | Yes | Summer | 700 | 546 | 57 | 276 | 3330 | 75 | Completed Delayed
MMTPL-2019-099 | Tata Steel | Steel | Kalinganagar, Odisha | Other (SMS) | Revamp | Revamp | Revamp of Other (SMS) equipment | 1978 | 911 | 229 | 183 | 2 | High | Yes | Monsoon | 346 | 215 | 32 | 274 | 1148 | 45 | Completed Delayed
MMTPL-2019-100 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Other (Smelter) | AMC | Maintenance | AMC of Other (Smelter) equipment | 300 | 208 | 365 | 137 | 1 | Low | Yes | Monsoon | 41 | 22 | 31 | 365 | 214 | 0 | Completed On-Time
MMTPL-2019-101 | SAIL | Steel | Bokaro, Jharkhand | Rolling Mill | Mechanical Erection | New Installation | Mechanical Erection of Rolling Mill equipment | 2101 | 1010 | 270 | 1181 | 2 | Medium | Yes | Summer | 312 | 218 | 63 | 253 | 960 | -17 | Completed On-Time
MMTPL-2019-102 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Other (Smelter) | AMC | Maintenance | AMC of Other (Smelter) equipment | 121 | 51 | 365 | 252 | 1 | Low | Yes | Monsoon | 23 | 13 | 46 | 365 | 53 | 0 | Completed On-Time
MMTPL-2019-103 | Hindalco | Metals & Alloys | Renukoot, UP | Other (Smelter) | AMC | Maintenance | AMC of Other (Smelter) equipment | 284 | 227 | 365 | 429 | 1 | Low | Yes | Summer | 34 | 28 | 73 | 365 | 236 | 0 | Completed On-Time
MMTPL-2019-104 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Rolling Mill | Shutdown Maintenance | Breakdown-Emergency | Shutdown Maintenance of Rolling Mill equipment | 714 | 497 | 25 | 1061 | 2 | Medium | Yes | Summer | 1143 | 800 | 59 | 30 | 598 | 5 | Completed Delayed
MMTPL-2019-105 | NTPC | Power | Korba, Chhattisgarh | Power-Boiler House | Mechanical Erection | Maintenance | Mechanical Erection of Power-Boiler House equipment | 1830 | 1252 | 182 | 1197 | 2 | High | Yes | Monsoon | 403 | 325 | 65 | 234 | 1612 | 52 | Completed Delayed
MMTPL-2019-106 | UltraTech Cement | Cement | Hirmi, Chhattisgarh | Material Handling | Structural Steel | Revamp | Structural Steel of Material Handling equipment | 953 | 430 | 121 | 351 | 1 | Medium | No | Summer | 158 | 92 | 70 | 119 | 434 | -2 | Completed On-Time
MMTPL-2019-107 | NTPC | Power | Vindhyachal, MP | Power-Boiler House | AMC | Maintenance | AMC of Power-Boiler House equipment | 127 | 77 | 365 | 211 | 1 | High | Yes | Summer | 25 | 18 | 68 | 365 | 77 | 0 | Completed On-Time
MMTPL-2019-108 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Rolling Mill | Mechanical Erection | New Installation | Mechanical Erection of Rolling Mill equipment | 5336 | 3647 | 483 | 873 | 1 | Medium | Yes | Summer | 221 | 147 | 73 | 448 | 3529 | -35 | Completed On-Time
MMTPL-2019-109 | Vedanta | Mining | Jharsuguda, Odisha | Material Handling | Mechanical Erection | Revamp | Mechanical Erection of Material Handling equipment | 990 | 502 | 130 | 971 | 2 | Low | Yes | Summer | 305 | 256 | 38 | 126 | 500 | -4 | Completed On-Time
MMTPL-2019-110 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Other (Smelter) | Fabrication & Erection | Maintenance | Fabrication & Erection of Other (Smelter) equipment | 701 | 297 | 128 | 218 | 2 | Low | Yes | Monsoon | 220 | 172 | 66 | 177 | 445 | 49 | Completed Delayed
MMTPL-2019-111 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Rolling Mill | Structural Steel | Revamp | Structural Steel of Rolling Mill equipment | 4324 | 2372 | 217 | 204 | 2 | Medium | No | Winter | 798 | 477 | 68 | 272 | 2846 | 55 | Completed Delayed
MMTPL-2020-112 | Hindalco | Metals & Alloys | Renukoot, UP | Rolling Mill | Revamp | Revamp | Revamp of Rolling Mill equipment | 1380 | 1022 | 200 | 769 | 1 | Medium | No | Monsoon | 138 | 86 | 48 | 46 | 651 | -154 | Terminated Early
MMTPL-2020-113 | Tata Steel | Steel | Kalinganagar, Odisha | Other (SMS) | Structural Steel | Revamp | Structural Steel of Other (SMS) equipment | 2791 | 1016 | 249 | 218 | 1 | High | Yes | Monsoon | 225 | 144 | 32 | 274 | 1163 | 25 | Completed Delayed
MMTPL-2020-114 | JSW Steel | Steel | Bellary, Karnataka | Sinter Plant | AMC | Maintenance | AMC of Sinter Plant equipment | 135 | 94 | 365 | 1083 | 1 | Medium | Yes | Winter | 49 | 35 | 40 | 365 | 90 | 0 | Completed On-Time
MMTPL-2020-115 | Vedanta | Mining | Jharsuguda, Odisha | Material Handling | Shutdown Maintenance | Breakdown-Emergency | Shutdown Maintenance of Material Handling equipment | 1252 | 886 | 34 | 774 | 3 | Medium | Yes | Monsoon | 1013 | 718 | 46 | 44 | 1207 | 10 | Completed Delayed
MMTPL-2020-116 | UltraTech Cement | Cement | Hirmi, Chhattisgarh | Material Handling | Shutdown Maintenance | Breakdown-Emergency | Shutdown Maintenance of Material Handling equipment | 449 | 167 | 48 | 1414 | 3 | Low | Yes | Winter | 562 | 416 | 56 | 55 | 186 | 7 | Completed Delayed
MMTPL-2020-117 | NTPC | Power | Vindhyachal, MP | Power-Boiler House | AMC | Maintenance | AMC of Power-Boiler House equipment | 85 | 47 | 365 | 1168 | 1 | High | Yes | Winter | 50 | 28 | 64 | 365 | 46 | 0 | Completed On-Time
MMTPL-2020-118 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Other (Smelter) | Shutdown Maintenance | Breakdown-Emergency | Shutdown Maintenance of Other (Smelter) equipment | 493 | 285 | 30 | 480 | 3 | Medium | No | Winter | 986 | 815 | 47 | 27 | 244 | -3 | Completed On-Time
MMTPL-2020-119 | Jindal Steel | Steel | Angul, Odisha | Other (SMS) | AMC | Maintenance | AMC of Other (SMS) equipment | 189 | 92 | 365 | 828 | 1 | High | No | Summer | 42 | 22 | 58 | 365 | 90 | 0 | Completed On-Time
MMTPL-2020-120 | Jindal Steel | Steel | Raigarh, Chhattisgarh | Sinter Plant | Fabrication & Erection | Revamp | Fabrication & Erection of Sinter Plant equipment | 2721 | 1003 | 233 | 1280 | 2 | Medium | Yes | Summer | 468 | 242 | 56 | 222 | 951 | -11 | Completed On-Time
MMTPL-2020-121 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Rolling Mill | AMC | Maintenance | AMC of Rolling Mill equipment | 247 | 91 | 365 | 1147 | 1 | Medium | No | Summer | 48 | 31 | 71 | 365 | 94 | 0 | Completed On-Time
MMTPL-2020-122 | AMNS India | Steel | Hazira, Gujarat | Coke Oven | Piping | Revamp | Piping of Coke Oven equipment | 984 | 616 | 286 | 495 | 1 | Medium | Yes | Winter | 69 | 54 | 32 | 392 | 855 | 106 | Completed Delayed
MMTPL-2020-123 | Vedanta | Mining | Jharsuguda, Odisha | Beneficiation Plant | AMC | Maintenance | AMC of Beneficiation Plant equipment | 296 | 217 | 365 | 612 | 1 | Low | Yes | Winter | 30 | 17 | 71 | 365 | 226 | 0 | Completed On-Time
MMTPL-2020-124 | NTPC | Power | Vindhyachal, MP | Power-Boiler House | Revamp | Revamp | Revamp of Power-Boiler House equipment | 4630 | 1835 | 209 | 250 | 2 | High | Yes | Winter | 887 | 688 | 66 | 233 | 2169 | 24 | Completed Delayed
MMTPL-2020-125 | AMNS India | Steel | Hazira, Gujarat | Other (SMS) | Revamp | Revamp | Revamp of Other (SMS) equipment | 3821 | 1312 | 199 | 1390 | 2 | High | Yes | Summer | 769 | 504 | 47 | 179 | 1130 | -20 | Completed On-Time
MMTPL-2020-126 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Rolling Mill | Piping | Revamp | Piping of Rolling Mill equipment | 3445 | 1140 | 267 | 262 | 1 | Medium | Yes | Summer | 259 | 157 | 37 | 363 | 1635 | 96 | Completed Delayed
MMTPL-2020-127 | Jindal Steel | Steel | Raigarh, Chhattisgarh | Other (SMS) | Fabrication & Erection | New Installation | Fabrication & Erection of Other (SMS) equipment | 3188 | 1681 | 394 | 1260 | 1 | High | Yes | Winter | 162 | 93 | 45 | 487 | 2180 | 93 | Completed Delayed
MMTPL-2020-128 | UltraTech Cement | Cement | Hirmi, Chhattisgarh | Other (Kiln) | Shutdown Maintenance | Breakdown-Emergency | Shutdown Maintenance of Other (Kiln) equipment | 259 | 85 | 51 | 1141 | 2 | Low | Yes | Summer | 204 | 153 | 61 | 48 | 80 | -3 | Completed On-Time
MMTPL-2020-129 | Tata Steel | Steel | Kalinganagar, Odisha | Blast Furnace | Structural Steel | New Installation | Structural Steel of Blast Furnace equipment | 9409 | 5475 | 362 | 1164 | 2 | High | Yes | Monsoon | 1040 | 730 | 32 | 483 | 7757 | 121 | Completed Delayed
MMTPL-2020-130 | Vedanta | Mining | Jharsuguda, Odisha | Beneficiation Plant | Shutdown Maintenance | Shutdown | Shutdown Maintenance of Beneficiation Plant equipment | 241 | 106 | 45 | 388 | 2 | Low | No | Winter | 215 | 172 | 54 | 62 | 147 | 17 | Completed Delayed
MMTPL-2020-131 | Vedanta | Mining | Jharsuguda, Odisha | Beneficiation Plant | AMC | Maintenance | AMC of Beneficiation Plant equipment | 270 | 127 | 365 | 385 | 1 | Medium | Yes | Winter | 44 | 22 | 49 | 365 | 131 | 0 | Completed On-Time
MMTPL-2020-132 | Hindalco | Metals & Alloys | Renukoot, UP | Other (Smelter) | Revamp | Revamp | Revamp of Other (Smelter) equipment | 2381 | 1126 | 153 | 584 | 2 | Low | No | Winter | 623 | 515 | 31 | 196 | 1503 | 43 | Completed Delayed
MMTPL-2020-133 | AMNS India | Steel | Hazira, Gujarat | Blast Furnace | Mechanical Erection | Revamp | Mechanical Erection of Blast Furnace equipment | 775 | 327 | 204 | 110 | 1 | High | Yes | Summer | 76 | 64 | 44 | 199 | 293 | -5 | Completed On-Time
MMTPL-2021-134 | UltraTech Cement | Cement | Hirmi, Chhattisgarh | Other (Kiln) | Fabrication & Erection | Maintenance | Fabrication & Erection of Other (Kiln) equipment | 786 | 398 | 193 | 583 | 1 | Low | Yes | Winter | 82 | 55 | 52 | 185 | 367 | -8 | Completed On-Time
MMTPL-2021-135 | Vedanta | Mining | Jharsuguda, Odisha | Material Handling | Structural Steel | New Installation | Structural Steel of Material Handling equipment | 5913 | 4004 | 342 | 989 | 1 | Low | No | Monsoon | 346 | 222 | 56 | 414 | 4646 | 72 | Completed Delayed
MMTPL-2021-136 | NTPC | Power | Korba, Chhattisgarh | Material Handling | Fabrication & Erection | Maintenance | Fabrication & Erection of Material Handling equipment | 1032 | 785 | 144 | 779 | 1 | Low | Yes | Summer | 144 | 75 | 67 | 181 | 943 | 37 | Completed Delayed
MMTPL-2021-137 | NTPC | Power | Korba, Chhattisgarh | Material Handling | Fabrication & Erection | Maintenance | Fabrication & Erection of Material Handling equipment | 1441 | 1107 | 63 | 260 | 1 | Medium | No | Winter | 458 | 353 | 54 | 86 | 1560 | 23 | Completed Delayed
MMTPL-2021-138 | Hindalco | Metals & Alloys | Renukoot, UP | Other (Smelter) | Piping | Maintenance | Piping of Other (Smelter) equipment | 2300 | 803 | 187 | 1499 | 2 | Medium | No | Monsoon | 492 | 284 | 39 | 223 | 990 | 36 | Completed Delayed
MMTPL-2021-139 | JSW Steel | Steel | Dolvi, Maharashtra | Other (SMS) | Shutdown Maintenance | Breakdown-Emergency | Shutdown Maintenance of Other (SMS) equipment | 704 | 327 | 24 | 797 | 2 | High | Yes | Summer | 1174 | 924 | 71 | 23 | 294 | -1 | Completed On-Time
MMTPL-2021-140 | Hindalco | Metals & Alloys | Renukoot, UP | Rolling Mill | AMC | Maintenance | AMC of Rolling Mill equipment | 253 | 120 | 365 | 306 | 1 | Medium | Yes | Monsoon | 40 | 33 | 63 | 365 | 124 | 0 | Completed On-Time
MMTPL-2021-141 | JSW Steel | Steel | Bellary, Karnataka | Blast Furnace | Revamp | Revamp | Revamp of Blast Furnace equipment | 552 | 398 | 195 | 493 | 1 | High | Yes | Summer | 57 | 40 | 72 | 98 | 208 | -97 | Terminated Early
MMTPL-2021-142 | UltraTech Cement | Cement | Hirmi, Chhattisgarh | Other (Kiln) | Mechanical Erection | New Installation | Mechanical Erection of Other (Kiln) equipment | 9719 | 2973 | 432 | 1104 | 2 | Medium | Yes | Monsoon | 900 | 703 | 41 | 297 | 2094 | -135 | Terminated Early
MMTPL-2021-143 | Tata Steel | Steel | Jamshedpur, Jharkhand | Other (SMS) | Fabrication & Erection | New Installation | Fabrication & Erection of Other (SMS) equipment | 4144 | 2932 | 467 | 567 | 2 | High | No | Summer | 355 | 205 | 73 | 582 | 4014 | 115 | Completed Delayed
MMTPL-2021-144 | Tata Steel | Steel | Jamshedpur, Jharkhand | Blast Furnace | Structural Steel | Maintenance | Structural Steel of Blast Furnace equipment | 1744 | 1078 | 181 | 1459 | 1 | High | Yes | Monsoon | 193 | 162 | 63 | 211 | 1378 | 30 | Completed Delayed
MMTPL-2021-145 | JSW Steel | Steel | Bellary, Karnataka | Sinter Plant | Revamp | Revamp | Revamp of Sinter Plant equipment | 4395 | 3349 | 159 | 1421 | 1 | Medium | No | Winter | 553 | 462 | 67 | 218 | 4578 | 59 | Completed Delayed
MMTPL-2021-146 | SAIL | Steel | Bokaro, Jharkhand | Rolling Mill | Mechanical Erection | Maintenance | Mechanical Erection of Rolling Mill equipment | 865 | 552 | 121 | 1127 | 2 | Medium | Yes | Winter | 286 | 240 | 33 | 117 | 520 | -4 | Completed On-Time
MMTPL-2021-147 | Tata Steel | Steel | Kalinganagar, Odisha | Sinter Plant | Revamp | Revamp | Revamp of Sinter Plant equipment | 1122 | 880 | 177 | 688 | 2 | Medium | Yes | Monsoon | 254 | 160 | 41 | 199 | 1021 | 22 | Completed Delayed
MMTPL-2021-148 | UltraTech Cement | Cement | Hirmi, Chhattisgarh | Material Handling | Revamp | Revamp | Revamp of Material Handling equipment | 2919 | 1916 | 294 | 188 | 1 | Medium | Yes | Winter | 199 | 105 | 49 | 348 | 2277 | 54 | Completed Delayed
MMTPL-2021-149 | Hindalco | Metals & Alloys | Renukoot, UP | Other (Smelter) | Mechanical Erection | New Installation | Mechanical Erection of Other (Smelter) equipment | 2430 | 1274 | 245 | 1156 | 2 | Medium | Yes | Summer | 397 | 252 | 48 | 308 | 1599 | 63 | Completed Delayed
MMTPL-2021-150 | Vedanta | Mining | Jharsuguda, Odisha | Beneficiation Plant | AMC | Maintenance | AMC of Beneficiation Plant equipment | 280 | 162 | 365 | 517 | 1 | Low | Yes | Summer | 35 | 19 | 40 | 365 | 158 | 0 | Completed On-Time
MMTPL-2021-151 | Vedanta | Mining | Jharsuguda, Odisha | Material Handling | Piping | Maintenance | Piping of Material Handling equipment | 515 | 397 | 152 | 1496 | 2 | Medium | Yes | Summer | 136 | 108 | 54 | 159 | 419 | 7 | Completed Delayed
MMTPL-2021-152 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Other (Smelter) | Structural Steel | Revamp | Structural Steel of Other (Smelter) equipment | 1615 | 971 | 166 | 1443 | 2 | Low | Yes | Summer | 390 | 262 | 66 | 154 | 904 | -12 | Completed On-Time
MMTPL-2021-153 | AMNS India | Steel | Hazira, Gujarat | Rolling Mill | Piping | Maintenance | Piping of Rolling Mill equipment | 1695 | 1010 | 89 | 1137 | 1 | Medium | Yes | Winter | 381 | 218 | 48 | 56 | 874 | -33 | Terminated Early
MMTPL-2021-154 | Tata Steel | Steel | Kalinganagar, Odisha | Rolling Mill | Fabrication & Erection | Revamp | Fabrication & Erection of Rolling Mill equipment | 2980 | 1875 | 151 | 1484 | 2 | Medium | Yes | Monsoon | 790 | 535 | 74 | 183 | 2295 | 32 | Completed Delayed
MMTPL-2021-155 | Vedanta | Mining | Jharsuguda, Odisha | Material Handling | AMC | Maintenance | AMC of Material Handling equipment | 279 | 197 | 365 | 1236 | 1 | Low | Yes | Summer | 40 | 28 | 66 | 365 | 194 | 0 | Completed On-Time
MMTPL-2022-156 | Vedanta | Mining | Jharsuguda, Odisha | Material Handling | Mechanical Erection | New Installation | Mechanical Erection of Material Handling equipment | 2615 | 1452 | 282 | 1082 | 1 | Low | Yes | Monsoon | 186 | 157 | 60 | 364 | 1822 | 82 | Completed Delayed
MMTPL-2022-157 | Tata Steel | Steel | Kalinganagar, Odisha | Rolling Mill | Mechanical Erection | New Installation | Mechanical Erection of Rolling Mill equipment | 3321 | 1565 | 328 | 443 | 2 | Medium | Yes | Monsoon | 405 | 245 | 75 | 424 | 2018 | 96 | Completed Delayed
MMTPL-2022-158 | Tata Steel | Steel | Jamshedpur, Jharkhand | Coke Oven | AMC | Maintenance | AMC of Coke Oven equipment | 77 | 49 | 365 | 356 | 1 | Medium | No | Winter | 25 | 15 | 57 | 365 | 47 | 0 | Completed On-Time
MMTPL-2022-159 | Hindalco | Metals & Alloys | Renukoot, UP | Other (Smelter) | AMC | Maintenance | AMC of Other (Smelter) equipment | 97 | 38 | 365 | 1366 | 1 | Medium | Yes | Winter | 38 | 24 | 30 | 365 | 36 | 0 | Completed On-Time
MMTPL-2022-160 | AMNS India | Steel | Hazira, Gujarat | Coke Oven | Revamp | Revamp | Revamp of Coke Oven equipment | 1012 | 708 | 237 | 1119 | 1 | Medium | Yes | Monsoon | 86 | 72 | 50 | 304 | 929 | 67 | Completed Delayed
MMTPL-2022-161 | UltraTech Cement | Cement | Hirmi, Chhattisgarh | Other (Kiln) | Shutdown Maintenance | Shutdown | Shutdown Maintenance of Other (Kiln) equipment | 812 | 494 | 37 | 1399 | 3 | Medium | No | Winter | 1317 | 742 | 74 | 40 | 531 | 3 | Completed Delayed
MMTPL-2022-162 | SAIL | Steel | Bokaro, Jharkhand | Rolling Mill | Structural Steel | Revamp | Structural Steel of Rolling Mill equipment | 1629 | 833 | 237 | 1016 | 2 | Medium | Yes | Winter | 275 | 165 | 41 | 217 | 705 | -20 | Completed On-Time
MMTPL-2022-163 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Rolling Mill | Revamp | Revamp | Revamp of Rolling Mill equipment | 3441 | 1267 | 92 | 806 | 2 | Medium | No | Winter | 1497 | 981 | 40 | 112 | 1629 | 20 | Completed Delayed
MMTPL-2022-164 | Tata Steel | Steel | Jamshedpur, Jharkhand | Sinter Plant | Piping | New Installation | Piping of Sinter Plant equipment | 5503 | 2113 | 265 | 956 | 2 | Medium | Yes | Monsoon | 831 | 654 | 53 | 288 | 2448 | 23 | Completed Delayed
MMTPL-2022-165 | NTPC | Power | Korba, Chhattisgarh | Material Handling | Shutdown Maintenance | Shutdown | Shutdown Maintenance of Material Handling equipment | 970 | 435 | 21 | 86 | 2 | Medium | Yes | Summer | 1415 | 1072 | 74 | 20 | 387 | -1 | Completed On-Time
MMTPL-2022-166 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Rolling Mill | Shutdown Maintenance | Shutdown | Shutdown Maintenance of Rolling Mill equipment | 523 | 305 | 28 | 1110 | 2 | Medium | Yes | Winter | 748 | 623 | 62 | 26 | 279 | -2 | Completed On-Time
MMTPL-2022-167 | Tata Steel | Steel | Jamshedpur, Jharkhand | Rolling Mill | Mechanical Erection | Maintenance | Mechanical Erection of Rolling Mill equipment | 2886 | 1226 | 92 | 1476 | 1 | Medium | Yes | Summer | 628 | 373 | 56 | 87 | 1143 | -5 | Completed On-Time
MMTPL-2022-168 | Vedanta | Mining | Jharsuguda, Odisha | Beneficiation Plant | AMC | Maintenance | AMC of Beneficiation Plant equipment | 253 | 187 | 365 | 210 | 1 | Medium | Yes | Monsoon | 34 | 28 | 50 | 365 | 194 | 0 | Completed On-Time
MMTPL-2022-169 | UltraTech Cement | Cement | Hirmi, Chhattisgarh | Material Handling | AMC | Maintenance | AMC of Material Handling equipment | 298 | 157 | 365 | 1380 | 1 | Medium | No | Winter | 46 | 26 | 47 | 365 | 164 | 0 | Completed On-Time
MMTPL-2022-170 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Other (Smelter) | Shutdown Maintenance | Shutdown | Shutdown Maintenance of Other (Smelter) equipment | 1259 | 940 | 46 | 119 | 3 | Low | Yes | Monsoon | 1233 | 616 | 57 | 34 | 371 | -12 | Terminated Early
MMTPL-2022-171 | AMNS India | Steel | Hazira, Gujarat | Coke Oven | Fabrication & Erection | Maintenance | Fabrication & Erection of Coke Oven equipment | 582 | 198 | 152 | 1380 | 2 | Medium | No | Summer | 154 | 100 | 35 | 147 | 194 | -5 | Completed On-Time
MMTPL-2022-172 | Tata Steel | Steel | Jamshedpur, Jharkhand | Sinter Plant | Structural Steel | New Installation | Structural Steel of Sinter Plant equipment | 3174 | 1776 | 453 | 931 | 1 | Medium | Yes | Winter | 141 | 94 | 44 | 612 | 2529 | 159 | Completed Delayed
MMTPL-2022-173 | Vedanta | Mining | Jharsuguda, Odisha | Beneficiation Plant | Mechanical Erection | Maintenance | Mechanical Erection of Beneficiation Plant equipment | 1705 | 837 | 136 | 292 | 1 | Low | Yes | Winter | 251 | 188 | 70 | 80 | 472 | -56 | Terminated Early
MMTPL-2022-174 | SAIL | Steel | Rourkela, Odisha | Other (SMS) | AMC | Maintenance | AMC of Other (SMS) equipment | 163 | 118 | 365 | 197 | 1 | High | No | Summer | 32 | 19 | 57 | 365 | 119 | 0 | Completed On-Time
MMTPL-2022-175 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Rolling Mill | Piping | Revamp | Piping of Rolling Mill equipment | 1190 | 820 | 153 | 1434 | 2 | Medium | Yes | Winter | 312 | 198 | 71 | 193 | 1011 | 40 | Completed Delayed
MMTPL-2022-176 | JSW Steel | Steel | Bellary, Karnataka | Rolling Mill | Structural Steel | New Installation | Structural Steel of Rolling Mill equipment | 4949 | 2791 | 405 | 44 | 1 | Medium | No | Monsoon | 245 | 181 | 60 | 505 | 3496 | 100 | Completed Delayed
MMTPL-2022-177 | Tata Steel | Steel | Jamshedpur, Jharkhand | Other (SMS) | Mechanical Erection | New Installation | Mechanical Erection of Other (SMS) equipment | 5295 | 4031 | 260 | 835 | 1 | High | Yes | Winter | 408 | 295 | 64 | 245 | 3647 | -15 | Completed On-Time
MMTPL-2023-178 | UltraTech Cement | Cement | Hirmi, Chhattisgarh | Other (Kiln) | Mechanical Erection | Maintenance | Mechanical Erection of Other (Kiln) equipment | 523 | 411 | 190 | 338 | 1 | Medium | Yes | Winter | 56 | 36 | 45 | 183 | 374 | -7 | Completed On-Time
MMTPL-2023-179 | JSW Steel | Steel | Bellary, Karnataka | Blast Furnace | Structural Steel | New Installation | Structural Steel of Blast Furnace equipment | 8428 | 3831 | 463 | 1367 | 1 | High | Yes | Summer | 365 | 245 | 52 | 130 | 1175 | -333 | Terminated Early
MMTPL-2023-180 | NTPC | Power | Vindhyachal, MP | Power-Boiler House | Piping | New Installation | Piping of Power-Boiler House equipment | 5403 | 3704 | 525 | 80 | 1 | High | Yes | Monsoon | 206 | 108 | 59 | 682 | 4987 | 157 | Completed Delayed
MMTPL-2023-181 | NTPC | Power | Vindhyachal, MP | Power-Boiler House | Structural Steel | Revamp | Structural Steel of Power-Boiler House equipment | 1867 | 798 | 184 | 230 | 1 | High | No | Winter | 203 | 162 | 45 | 225 | 933 | 41 | Completed Delayed
MMTPL-2023-182 | JSW Steel | Steel | Dolvi, Maharashtra | Coke Oven | Structural Steel | New Installation | Structural Steel of Coke Oven equipment | 3932 | 2266 | 589 | 1482 | 1 | Medium | Yes | Monsoon | 134 | 105 | 66 | 807 | 3098 | 218 | Completed Delayed
MMTPL-2023-183 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Rolling Mill | Fabrication & Erection | New Installation | Fabrication & Erection of Rolling Mill equipment | 9450 | 3160 | 173 | 972 | 2 | Medium | No | Monsoon | 1288 | 997 | 69 | 182 | 3258 | 9 | Completed Delayed
MMTPL-2023-184 | AMNS India | Steel | Hazira, Gujarat | Coke Oven | Shutdown Maintenance | Breakdown-Emergency | Shutdown Maintenance of Coke Oven equipment | 500 | 187 | 49 | 859 | 2 | Medium | Yes | Winter | 409 | 204 | 72 | 48 | 190 | -1 | Completed On-Time
MMTPL-2023-185 | Vedanta | Mining | Jharsuguda, Odisha | Beneficiation Plant | Fabrication & Erection | Revamp | Fabrication & Erection of Beneficiation Plant equipment | 2451 | 1913 | 197 | 311 | 2 | Medium | Yes | Summer | 498 | 418 | 35 | 255 | 2490 | 58 | Completed Delayed
MMTPL-2023-186 | UltraTech Cement | Cement | Hirmi, Chhattisgarh | Material Handling | AMC | Maintenance | AMC of Material Handling equipment | 259 | 128 | 365 | 1232 | 1 | Low | Yes | Summer | 30 | 24 | 55 | 365 | 124 | 0 | Completed On-Time
MMTPL-2023-187 | Lloyds Metals | Metals & Alloys | Chandrapur, Maharashtra | Other (Smelter) | Piping | New Installation | Piping of Other (Smelter) equipment | 2223 | 1533 | 253 | 1217 | 1 | Low | Yes | Summer | 176 | 135 | 58 | 276 | 1678 | 23 | Completed Delayed
MMTPL-2023-188 | Jindal Steel | Steel | Raigarh, Chhattisgarh | Coke Oven | Revamp | Revamp | Revamp of Coke Oven equipment | 1482 | 1043 | 113 | 643 | 1 | Medium | No | Winter | 263 | 196 | 52 | 152 | 1364 | 39 | Completed Delayed
MMTPL-2023-189 | Vedanta | Mining | Jharsuguda, Odisha | Material Handling | Piping | New Installation | Piping of Material Handling equipment | 1509 | 872 | 357 | 1146 | 2 | Low | Yes | Summer | 170 | 143 | 38 | 376 | 986 | 19 | Completed Delayed
MMTPL-2023-190 | AMNS India | Steel | Hazira, Gujarat | Coke Oven | AMC | Maintenance | AMC of Coke Oven equipment | 211 | 162 | 365 | 192 | 1 | Medium | Yes | Monsoon | 22 | 12 | 71 | 365 | 155 | 0 | Completed On-Time
MMTPL-2023-191 | Hindalco | Metals & Alloys | Renukoot, UP | Rolling Mill | Revamp | Revamp | Revamp of Rolling Mill equipment | 3216 | 2479 | 121 | 123 | 1 | Medium | Yes | Winter | 532 | 345 | 52 | 114 | 2236 | -7 | Completed On-Time
MMTPL-2023-192 | AMNS India | Steel | Hazira, Gujarat | Coke Oven | Piping | Maintenance | Piping of Coke Oven equipment | 808 | 503 | 68 | 1041 | 1 | Medium | Yes | Winter | 238 | 172 | 63 | 80 | 599 | 12 | Completed Delayed
MMTPL-2023-193 | AMNS India | Steel | Hazira, Gujarat | Rolling Mill | Revamp | Revamp | Revamp of Rolling Mill equipment | 3441 | 1624 | 212 | 1178 | 2 | Medium | Yes | Monsoon | 650 | 509 | 47 | 266 | 1944 | 54 | Completed Delayed
MMTPL-2023-194 | JSW Steel | Steel | Dolvi, Maharashtra | Other (SMS) | Piping | Revamp | Piping of Other (SMS) equipment | 2406 | 1019 | 130 | 513 | 1 | High | Yes | Winter | 371 | 289 | 52 | 119 | 957 | -11 | Completed On-Time
MMTPL-2023-195 | SAIL | Steel | Bhilai, Chhattisgarh | Sinter Plant | Shutdown Maintenance | Breakdown-Emergency | Shutdown Maintenance of Sinter Plant equipment | 834 | 543 | 52 | 740 | 2 | Medium | No | Winter | 642 | 539 | 64 | 51 | 544 | -1 | Completed On-Time
MMTPL-2023-196 | Jindal Steel | Steel | Angul, Odisha | Rolling Mill | Mechanical Erection | New Installation | Mechanical Erection of Rolling Mill equipment | 1920 | 595 | 269 | 998 | 1 | Medium | Yes | Winter | 143 | 113 | 50 | 349 | 839 | 80 | Completed Delayed
MMTPL-2023-197 | JSW Steel | Steel | Bellary, Karnataka | Sinter Plant | Shutdown Maintenance | Shutdown | Shutdown Maintenance of Sinter Plant equipment | 327 | 255 | 48 | 785 | 3 | Medium | Yes | Winter | 409 | 227 | 57 | 55 | 283 | 7 | Completed Delayed
MMTPL-2023-198 | Hindalco | Metals & Alloys | Renukoot, UP | Rolling Mill | AMC | Maintenance | AMC of Rolling Mill equipment | 297 | 172 | 365 | 1276 | 1 | Medium | No | Summer | 32 | 19 | 74 | 365 | 177 | 0 | Completed On-Time
MMTPL-2023-199 | Jindal Steel | Steel | Angul, Odisha | Sinter Plant | AMC | Maintenance | AMC of Sinter Plant equipment | 50 | 38 | 365 | 1193 | 1 | Medium | Yes | Winter | 50 | 35 | 70 | 204 | 32 | -161 | Terminated Early
MMTPL-2024-200 | UltraTech Cement | Cement | Hirmi, Chhattisgarh | Other (Kiln) | Fabrication & Erection | Maintenance | Fabrication & Erection of Other (Kiln) equipment | 518 | 409 | 120 | 363 | 2 | Low | No | Winter | 173 | 101 | 34 | 113 | 361 | -7 | Completed On-Time

## Data_Dictionary
Column | Type | Data type | Description | Allowed / example values
Contract_ID | Feature | Text | Unique internal ID for the contract | MMTPL-2022-014
Client_Name | Feature | Text | Company that awarded the contract | JSW Steel, Lloyds Metals, Vedanta
Client_Industry | Feature | Category | Sector the client operates in | Steel / Mining / Cement / Power / Metals & Alloys / Infrastructure / Other
Plant_Location | Feature | Text | Site city/state | Bellary, Karnataka
Plant_Unit_Type | Feature | Category | The specific plant unit the work is on — a strong driver of complexity | Blast Furnace / Sinter Plant / Coke Oven / Rolling Mill / Beneficiation Plant / Power-Boiler House / Material Handling / Other
Contract_Type | Feature | Category | Nature of the mechanical work itself | Mechanical Erection / Fabrication & Erection / Piping / Structural Steel / Shutdown Maintenance / AMC / Revamp
Contract_Nature | Feature | Category | Whether this is new build vs. ongoing/repair work | New Installation / Maintenance / Shutdown / Revamp / Breakdown-Emergency
Scope_Summary | Feature | Text | One-line description of what was erected/built (not used directly by the model, useful for your own reference and later text-based features) | Erection of sinter cooler and structural steel
Est_Equipment_Weight_Tons | Feature | Number | Estimated total tonnage of equipment/structure — usually the single biggest driver of manpower need | 850
Est_Contract_Value_INR_Lakhs | Feature | Number | Contract value quoted/awarded, in INR Lakhs | 420
Planned_Duration_Days | Feature | Number | Duration committed to the client at award | 150
Site_Distance_From_Base_KM | Feature | Number | Distance from MMTPL's base/nearest hub — affects mobilization lead time and cost | 65
Shifts_Planned | Feature | Number (1/2/3) | Planned working shifts per day | 2
Safety_Risk_Level | Feature | Category | Hot work / height / confined space risk profile | Low / Medium / High
Repeat_Client | Feature | Category | Whether MMTPL has worked with this client before | Yes / No
Season_of_Start | Feature | Category | Season the contract began in — monsoon affects productivity in many sites | Summer / Monsoon / Winter
Actual_Peak_Manpower | Target | Number | Highest daily headcount on site at any point | 145
Actual_Avg_Monthly_Manpower | Target | Number | Average monthly headcount across the contract | 95
Skilled_Manpower_Percent | Target | Number (0-100) | Share of workforce that was skilled (fitters, welders, riggers, electricians) vs. unskilled labour | 60
Actual_Duration_Days | Target | Number | Actual days taken to complete | 168
Actual_Cost_INR_Lakhs | Target | Number | Actual total cost incurred, INR Lakhs | 468
Delay_Days | Target | Number | Actual_Duration_Days minus Planned_Duration_Days (negative = finished early) | 18
Contract_Outcome | Target | Category | Final status | Completed On-Time / Completed Delayed / Terminated Early / Ongoing